## Sheet1
'Hopes & Screams' Production Pipeline
PRE-PROD. | Week | Date | Event | Nick | Red | Emma | Cait | Emily
| 5 | Fri 26th Oct. | Crew Meeting 5pm | Finish character designs | Finish character designs | Admin, Sound, Blog, Anim. Tests | Script, Treatment, Outline | Finish Storyboards & BGs
| 6 | Tues 30th Oct. | Pitch | Attend | PRESENT | PRESENT | Attend | Attend
| 7 | Tues 6th Nov. | Final Pitch | Attend | Attend | Attend | Attend | Attend
| 7 | Fri 9th Nov. | Crew Meeting 5pm | Complete designs | Complete designs & rec. sounds | Complete admin & rec. sounds | Complete writing | Complete BGs
PRODUCTION | 8 | Mon 12th Nov. | First Animating Day | Start scene 5 | Start scenes 15 & 16 | Start scene 1 | Start scene 3 | Start scene 7
| 9 | Mon 19th Nov. | Crew Meeting 10am | Present scene 5 | Present scene 15, show 16 prog. | Show scene 1 progress | Present scene 3 | Present scene 7
| 10 | Mon 26th Nov. | Crew Meeting 10am | Present scene 6 | Present scene 16, show 17 prog. | Present scene 1 | Present scenes 4 & 11 | Present scene 8
| 11 | Mon 3rd Dec. | Crew Meeting 10am | Present scene 12 | Present scene 17, show 18 prog. | Present scene 2 | Present scene 9 | Show scene 13 progress
| 12 | Mon 10th Dec. | Crew Meeting 10am | Present scene 22 | Present scenes 18, 19, 20 (21 prog.) | Present scene 24 | Present scene 10 | Present scene 13
| 12 | Fri 14th Dec. | Last Anim. Day, CM 5pm | Present scene 23 | Present scene 21 | Present scene 25 | Colour | Present scene 14 | < ALL HAND SCENES TO EMMA
POST-PROD. | CHRISTMAS | Before 25th Dec. | Post - Production | Work on blog & sketchbook | Record missing sounds | Edit film, tie up loose ends | Work on Production Bible | Work on titles & credits
| CHRISTMAS | Before 8th Jan. | Post - Production | Complete blog and sketchbook | Finish recording sounds | Prepare film for burning | Complete Production Bible | Complete titles & credits
| 13 | Weds 9th Jan. | Crew Meeting 10am | Complete Project*** | Complete Project | Complete Project | Complete Project | Complete Project
| 14 | Tues 15th Jan. | Final Assessment | PRESENT | PRESENT | PRESENT | PRESENT | PRESENT
*** = Burn DVD, complete Prod. Bible, complete blog, finalise sketchbooks etc.
Scenes
|  |  | 1. Vampire Front | 14. Spotlight CU
|  |  | 2. Vampire Reflection | 15. Knight Sees Castle
|  |  | 3. Man On Loo | 16. Knight Climbs Up
|  |  | 4. Spotting Paper | 17. Knight Comes In
|  |  | 5. Grabbing Paper CU | 18. Dragon Reveal
|  |  | 6. Grabbing Paper WS | 19. Princess Wink
|  |  | 7. T Rex WS | 20. Dragon CU
|  |  | 8. T Rex Trample | 21. Knight Blushes
|  |  | 9. T Rex Turn | 22. Final Loo Tug
|  |  | 10. T Rex Bloodbath | 23. Mummy Under
|  |  | 11. T Rex Whimper | 24. Pervy Wipe
|  |  | 12. Loo Pan & Grab | 25. Knight Reprise
13. Spotlight WS